## Report
Action Para Details :-
Supervised Entity Name | Sr.No. | Action para Id | Action Para Description/Observation | Actual Due Date | Extended Due Date | Response Type | Is Resubmission Required | SE Status | Status | Regulatory Internal Comments By RBI | Regulatory Compliance Level Comments By RBI | Internal Comments By SSM And Higher Authority | Compliance Level Comments By SSM And Higher Authority | SE Response1 | 1st SSM Comment for SE | SE Response2 | 2nd SSM Comment for SE | SE Response3 | 3rd SSM Comment for SE | SE Response4 | 4th SSM Comment for SE | SE Response5 | 5th SSM Comment for SE | SE Response6 | 6th SSM Comment for SE | SE Response7 | 7th SSM Comment for SE | SE Response8 | 8th SSM Comment for SE | SE Response9 | 9th SSM Comment for SE | SE Response10 | 10th SSM Comment for SE | SE Response11 | 11th SSM Comment for SE | SE Response12 | 12th SSM Comment for SE | SE Response13 | 13th SSM Comment for SE | SE Response14 | 14th SSM Comment for SE | SE Response15 | 15th SSM Comment for SE
Himgiri Local Area Bank Limited | 1 | 3.1.1 | Board / management oversight of IT and cyber risk was informal and the information-security policy was not periodically reviewed. | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Himgiri Local Area Bank Limited | 2 | 3.2.1 | Patching was ad hoc, several endpoints lacked centrally managed anti-malware, and email-security controls were basic. | 29/01/2026 |  | Text | No | Complied | Complied
Himgiri Local Area Bank Limited | 3 | 3.2.2 | Two-factor authentication was not enforced for all privileged / CBS access and access reviews were infrequent. | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Himgiri Local Area Bank Limited | 4 | 3.3.1 | The arrangement with the CBS vendor lacked documented security obligations, service levels and an exit / continuity plan. | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Himgiri Local Area Bank Limited | 5 | 3.4.1 | A documented BCP / DR plan was not in place and backup restoration was not tested. | 29/01/2026 |  | Text | No | Complied | Complied
Himgiri Local Area Bank Limited | 6 | 3.5.1 | IS audit was limited in scope and not conducted at an adequate frequency. | 29/01/2026 |  | Text | No | Not Complied | Not Complied