## Report
Action Para Details :-
Supervised Entity Name | Sr.No. | Action para Id | Action Para Description/Observation | Actual Due Date | Extended Due Date | Response Type | Is Resubmission Required | SE Status | Status | Regulatory Internal Comments By RBI | Regulatory Compliance Level Comments By RBI | Internal Comments By SSM And Higher Authority | Compliance Level Comments By SSM And Higher Authority | SE Response1 | 1st SSM Comment for SE | SE Response2 | 2nd SSM Comment for SE | SE Response3 | 3rd SSM Comment for SE | SE Response4 | 4th SSM Comment for SE | SE Response5 | 5th SSM Comment for SE | SE Response6 | 6th SSM Comment for SE | SE Response7 | 7th SSM Comment for SE | SE Response8 | 8th SSM Comment for SE | SE Response9 | 9th SSM Comment for SE | SE Response10 | 10th SSM Comment for SE | SE Response11 | 11th SSM Comment for SE | SE Response12 | 12th SSM Comment for SE | SE Response13 | 13th SSM Comment for SE | SE Response14 | 14th SSM Comment for SE | SE Response15 | 15th SSM Comment for SE
Pragati Co-operative Bank Limited | 1 | 3.1.1 | The Board had limited IT / cyber expertise and the CISO, though designated, also held operational IT responsibilities, diluting independence. | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Pragati Co-operative Bank Limited | 2 | 3.1.2 | No Board-approved SOP / policy was in place for the CBS migration carried out during the period; a post-migration audit identified discrepancies in balances and funds parked in multiple migration GL heads, which were not reconciled as on the date of examination. | 29/01/2026 |  | Text | No | Complied | Complied
Pragati Co-operative Bank Limited | 3 | 3.1.3 | The Digital Payment Security Controls Policy did not articulate the digital payment cycle and exception handling per product, which was non-adherence to para 4 of Chapter II of the DPSC Master Direction. | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Pragati Co-operative Bank Limited | 4 | 3.2.1 | Five observations including a High-risk observation (database security) from the previous IS audit were open as on the date of examination. | 29/01/2026 |  | Text | No | Complied | Not Complied
Pragati Co-operative Bank Limited | 5 | 3.3.1 | The following End-of-Life / End-of-Support systems were active in the environment without an upgrade / replacement plan: | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Pragati Co-operative Bank Limited | 6 | 3.3.2 | The CBS application was not included in the application inventory and the inventory did not capture whether hosted applications were public-facing or internal. | 29/01/2026 |  | Text | No | Complied | Not Complied
Pragati Co-operative Bank Limited | 7 | 3.4.1 | Access to the internet / MPLS core routers was not restricted to specific IP addresses and was allowed to the entire subnet of the bank's network. | 29/01/2026 |  | Text | No | Complied | Complied
Pragati Co-operative Bank Limited | 8 | 3.4.2 | Perimeter firewalls were running with outdated firmware and multiple firewall rules with destination ‘ANY’ / insecure ports were configured without justification. | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Pragati Co-operative Bank Limited | 9 | 3.5.1 | Secure Configuration Documents were not defined for several network devices, security solutions and middleware, and periodic configuration review was not performed against the defined periodicity. | 29/01/2026 |  | Text | No | Complied | Not Complied
Pragati Co-operative Bank Limited | 10 | 3.6.1 | Vulnerabilities identified in the source-code review were not closed within the defined timelines and were open as on the date of examination. | 29/01/2026 |  | Text | No | Complied | Complied
Pragati Co-operative Bank Limited | 11 | 3.6.2 | PII such as PAN and mobile number was not masked in the databases of Internet Banking, Mobile Banking and the CBS. | 29/01/2026 |  | Text | No | Complied | Not Complied
Pragati Co-operative Bank Limited | 12 | 3.7.1 | Third-party application software and middleware were not tracked under patch management and a centralized change-management function was not established. | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Pragati Co-operative Bank Limited | 13 | 3.8.1 | Access-control matrices for network / security devices were not maintained, periodic access review was not performed, and the email-gateway / DLP solutions were not integrated with the PAM solution with MFA for administrators. | 29/01/2026 |  | Text | No | Complied | Not Complied
Pragati Co-operative Bank Limited | 14 | 3.9.1 | NDA / SLA were not signed for several IT service providers, and source-code escrow / a documented exit plan for the CBS vendor was not in place. | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Pragati Co-operative Bank Limited | 15 | 3.10.1 | The C-SOC was not fully operational with 24x7 monitoring and defined use-cases; TAT for incident / alert closure was not defined and a large number of XDR alerts remained open. | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Pragati Co-operative Bank Limited | 16 | 3.10.2 | Critical applications and CBS privileged-user logs were not fully integrated with the SIEM solution. | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Pragati Co-operative Bank Limited | 17 | 3.11.1 | RBTM alerts for certain channels (RTGS / NEFT, Internet / Mobile Banking) were not integrated and ATM-channel alerts were monitored at T-1 rather than in real time. | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Pragati Co-operative Bank Limited | 18 | 3.11.2 | 24x7 monitoring of FRM alerts was not enabled; alerts generated during off-business hours were left unattended till the next working day. | 29/01/2026 |  | Text | No | Complied | Not Complied
Pragati Co-operative Bank Limited | 19 | 3.12.1 | DR drills were conducted but recovery objectives (RTO / RPO) were not formally validated and signed off. | 29/01/2026 |  | Text | No | Complied | Not Complied