## Report
Action Para Details :-
Supervised Entity Name | Sr.No. | Action para Id | Action Para Description/Observation | Actual Due Date | Extended Due Date | Response Type | Is Resubmission Required | SE Status | Status | Regulatory Internal Comments By RBI | Regulatory Compliance Level Comments By RBI | Internal Comments By SSM And Higher Authority | Compliance Level Comments By SSM And Higher Authority | SE Response1 | 1st SSM Comment for SE | SE Response2 | 2nd SSM Comment for SE | SE Response3 | 3rd SSM Comment for SE | SE Response4 | 4th SSM Comment for SE | SE Response5 | 5th SSM Comment for SE | SE Response6 | 6th SSM Comment for SE | SE Response7 | 7th SSM Comment for SE | SE Response8 | 8th SSM Comment for SE | SE Response9 | 9th SSM Comment for SE | SE Response10 | 10th SSM Comment for SE | SE Response11 | 11th SSM Comment for SE | SE Response12 | 12th SSM Comment for SE | SE Response13 | 13th SSM Comment for SE | SE Response14 | 14th SSM Comment for SE | SE Response15 | 15th SSM Comment for SE
Bharat Mercantile Bank Limited | 1 | 3.1.1 | The Board-level IT Strategy Committee met thrice during the year against the prescribed quarterly cadence and one member did not possess substantial IT / cyber expertise, which was non-adherence to the IT Strategy Committee provisions of the IT Governance, Risk, Controls and Assurance Practices Directions, 2023. | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Bharat Mercantile Bank Limited | 2 | 3.1.2 | The IT Steering Committee minutes did not consistently track project-level risk, budget variance and benefit realisation for material IT projects. | 29/01/2026 |  | Text | No | Complied | Not Complied
Bharat Mercantile Bank Limited | 3 | 3.1.3 | The ‘Digital Payment Security Controls Policy’ did not include the mechanics, clear definition of the starting point, critical intermittent stages and end point of the digital payment cycle, validations and exception handling for every digital payment product, which was non-adherence to para 4 of Chapter II of the DPSC Master Direction dated February 18, 2021. | 29/01/2026 |  | Text | No | Complied | Not Complied
Bharat Mercantile Bank Limited | 4 | 3.2.1 | Five observations of the FY 2023-24 IS audit, including one High-risk observation pertaining to database security, were open as on the date of IT Examination; the closure of prior observations was not tracked to root-cause. | 29/01/2026 |  | Text | No | Complied | Not Complied
Bharat Mercantile Bank Limited | 5 | 3.3.1 | The centralized IT asset inventory was not Board / management approved and version-control history (reviewer / approver) was not captured. | 29/01/2026 |  | Text | No | Complied | Not Complied
Bharat Mercantile Bank Limited | 6 | 3.3.2 | The following End-of-Life / End-of-Support (EOL/S) systems were active in the environment without a documented upgrade / replacement plan: | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Bharat Mercantile Bank Limited | 7 | 3.4.1 | Multiple firewall rules with destination ‘ANY’ were configured without business justification (sample rule IDs 10, 63, 234) and insecure HTTP / FTP ports were permitted on several rules. | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Bharat Mercantile Bank Limited | 8 | 3.4.2 | The perimeter firewalls were running on outdated firmware (n-3) against the latest available release. | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Bharat Mercantile Bank Limited | 9 | 3.5.1 | Secure Configuration Documents (SCD) were not defined for middleware and several security solutions, and periodic configuration review was not performed against the defined half-yearly periodicity in the Information Security Policy. | 29/01/2026 |  | Text | No | Complied | Not Complied
Bharat Mercantile Bank Limited | 10 | 3.6.1 | The source-code review of a critical application conducted in the period was not remediated; all identified vulnerabilities were open as on the date of examination against the defined closure timelines (15 / 30 / 60 days). | 29/01/2026 |  | Text | No | Complied | Not Complied
Bharat Mercantile Bank Limited | 11 | 3.6.2 | Personally Identifiable Information (PII) such as PAN and mobile number was not masked in the databases of Internet Banking, Mobile Banking and the CBS. | 29/01/2026 |  | Text | No | Complied | Not Complied
Bharat Mercantile Bank Limited | 12 | 3.7.1 | Third-party application software (e.g., Adobe Reader, MS Office, 7-Zip) and middleware (IIS, Apache Tomcat) installed on servers / endpoints were not tracked under the patch-management cycle. | 29/01/2026 |  | Text | No | Complied | Not Complied
Bharat Mercantile Bank Limited | 13 | 3.7.2 | A centralized change-management function was not established; emergency changes were processed without consistent post-implementation review. | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Bharat Mercantile Bank Limited | 14 | 3.8.1 | Shared administrator accounts were in use on two critical servers and the email-gateway / DLP solutions were not integrated with the PAM solution for centralized authentication; MFA was not configured for administrator users. | 29/01/2026 |  | Text | No | Complied | Not Complied
Bharat Mercantile Bank Limited | 15 | 3.8.2 | Periodic user-access review was not performed for network and security devices. | 29/01/2026 |  | Text | No | Complied | Not Complied
Bharat Mercantile Bank Limited | 16 | 3.9.1 | Non-Disclosure Agreements (NDA) / Service-Level Agreements (SLA) were not on record for two material IT service providers. | 29/01/2026 |  | Text | No | Complied | Complied
Bharat Mercantile Bank Limited | 17 | 3.9.2 | Customer-facing workloads were concentrated with a single cloud service provider and a documented, tested exit / portability arrangement was not in place. | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Bharat Mercantile Bank Limited | 18 | 3.10.1 | The SIEM had onboarded approximately 70% of critical assets; turnaround time (TAT) for alert closure was not defined and a large backlog of open alerts was observed in the EDR / XDR solution. | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Bharat Mercantile Bank Limited | 19 | 3.11.1 | Transaction monitoring was predominantly static rule-based and a cooling period was not consistently applied on certain beneficiary / limit changes; behavioural analytics were not implemented. | 29/01/2026 |  | Text | No | Complied | Complied
Bharat Mercantile Bank Limited | 20 | 3.12.1 | CAPTCHA was implemented only after two unsuccessful login attempts and an additional layer of authentication was not implemented at login, which was non-adherence to para 51 of Chapter III of the DPSC Master Direction. | 29/01/2026 |  | Text | No | Complied | Not Complied
Bharat Mercantile Bank Limited | 21 | 3.12.2 | Validity was not set for system-generated passwords dispatched to customers, which was non-adherence to para 53 of Chapter III of the DPSC Master Direction. | 29/01/2026 |  | Text | No | Complied | Not Complied
Bharat Mercantile Bank Limited | 22 | 3.13.1 | The last full-scale DR drill was conducted 14 months prior and recovery objectives (RTO / RPO) for internet and mobile banking were not validated end-to-end. | 29/01/2026 |  | Text | No | Complied | Complied