Bharat Mercantile Bank Limited

IT Steering Committee – Standard Operating Procedure (SOP)

Document Reference: BMBL/ITGC/SOP/ITSC/003

Version: 1.2

Effective Date: 01 June 2024

Review Cycle: Semi-Annual

Owner: Chief Information Officer

Approved By: IT Strategy Committee – Resolution No. ITSC/2024/015

Document Control

| Version | Date | Author | Description of Change |
| --- | --- | --- | --- |
| 1.0 | 10 Jan 2024 | IT Governance Cell | Initial SOP |
| 1.1 | 15 Mar 2024 | PMO | Updated project risk tracking thresholds |
| 1.2 | 25 May 2024 | CIO | Added benefit realisation tracking per RBI guideline |

1. Purpose and Scope

This Standard Operating Procedure (SOP) defines the operational framework, meeting protocols, project governance mechanisms, and reporting standards for the IT Steering Committee (ITSC) of Bharat Mercantile Bank Limited. The SOP governs all material IT projects, including new product development, infrastructure upgrades, digital platform implementations, and regulatory technology initiatives.

Scope: All IT projects with:

Budget exceeding INR 2 Crore

Timeline exceeding 6 months

Critical business impact rating

Regulatory compliance dependencies

Third-party/vendor-led implementations

2. Committee Composition

| Role | Designation | Responsibility |
| --- | --- | --- |
| Chairman | Chief Information Officer | Preside over meetings, ensure agenda coverage |
| Member | Chief Financial Officer | Budget approval, cost-benefit analysis |
| Member | Chief Risk Officer | Risk assessment, mitigation oversight |
| Member | Head – Digital Banking | Digital product oversight |
| Member | Head – Operations | Operational impact assessment |
| Member | Head – Compliance | Regulatory compliance verification |
| Invitee | Project Managers (as applicable) | Project status presentation |
| Invitee | Vendor Representatives (as applicable) | Technical input |
| Secretary | PMO Lead | Minutes, action tracking, documentation |

3. Meeting Governance

3.1 Meeting Frequency

| Meeting Type | Frequency | Duration | Purpose |
| --- | --- | --- | --- |
| Regular Review | Monthly | 90 minutes | Ongoing project portfolio review |
| Milestone Review | As required per project plan | 60 minutes per project | Stage-gate approvals |
| Emergency Meeting | On-demand (24 hr notice) | As required | Critical issues, breaches, escalations |
| Quarterly Deep-Dive | Quarterly | Half-day | Strategic alignment & benefit realisation |

3.2 Quorum

| Condition | Requirement |
| --- | --- |
| Minimum Members | 4 of 6 members |
| Mandatory Attendees | CIO and CRO (or authorised representatives) |
| Project-Specific Quorum | Sponsor and Project Manager for relevant agenda item |
| Decision Validity | Unanimity for high-risk decisions; majority for routine decisions |

3.3 Agenda and Minutes

| Item | Timeline | Responsible |
| --- | --- | --- |
| Agenda Circulation | 5 working days before meeting | PMO Lead |
| Additional Agenda Items | 2 working days before meeting | Any member |
| Minutes Circulation | 3 working days after meeting | PMO Lead |
| Action Item Status Update | Within 7 days of target date | Respective owner |
| Minutes Archival | Within 10 days of meeting (e-signature) | PMO Lead |

4. Project Risk Tracking Framework

4.1 Risk Classification

Every material IT project shall maintain a Project Risk Register classified under the following categories:

| Risk Category | Weight | Examples |
| --- | --- | --- |
| Technology Risk | 25% | Platform obsolescence, integration failure, scalability issues |
| Operational Risk | 20% | Process disruption, change management failure |
| Vendor Risk | 15% | Vendor insolvency, SLA breach, IP disputes |
| Regulatory Risk | 15% | Non-compliance with RBI directives, data localisation issues |
| Cyber Risk | 15% | Data breach, unauthorised access, ransomware |
| Resource Risk | 10% | Key personnel attrition, skill gaps |

4.2 Risk Scoring Matrix

| Score | Rating | Definition | Action Required |
| --- | --- | --- | --- |
| 1 | Very Low | Negligible impact, rare probability | Monitor |
| 2 | Low | Minor impact, unlikely | Include in project risk log |
| 3 | Medium | Moderate impact, possible | Mitigation plan required |
| 4 | High | Major impact, likely | Escalate to ITSC |
| 5 | Critical | Severe impact, almost certain | Escalate to IT Strategy Committee / Board |

4.3 Risk Dashboard Reporting

Each ITSC meeting shall include a Project Risk Dashboard with:

| Data Point | Format | Update Frequency |
| --- | --- | --- |
| Current risk score (RAG) | Red / Amber / Green | Monthly |
| Risk trend (last 3 periods) | Improving / Stable / Deteriorating | Monthly |
| Top 5 risks by project | Narrative | Monthly |
| Risk mitigation status | % complete vs target | Monthly |
| Escalated risks & resolution | Tracker | Every meeting |

RAG Thresholds:

Green: Average risk score ≤ 2.0, no score > 3

Amber: Average risk score 2.1 – 3.5, or any single score = 4

Red: Average risk score > 3.5, or any single score = 5

5. Budget Variance Tracking

5.1 Budget Categorisation

| Budget Head | Description | Variance Tolerance |
| --- | --- | --- |
| Capital Expenditure (CapEx) | Hardware, software licenses, IP acquisition | +/- 10% |
| Operational Expenditure (OpEx) | Cloud services, AMC, consulting | +/- 15% |
| Resource Cost | Internal staffing, contractors | +/- 10% |
| Contingency Reserve | Unforeseen expenses (5% of total budget) | +/- 20% of contingency |
| Change Requests | Scope changes approved by ITSC | As approved |

5.2 Variance Reporting

| Variance % | Status | Action Required |
| --- | --- | --- |
| 0% – 5% | On Track | No action |
| 5% – 10% | Watch | Explanation in minutes |
| 10% – 15% | Alert | Recovery plan required |
| > 15% | Critical | Immediate ITSC review, project review |

5.3 Budget Reporting Format

For each material IT project, the following budget information shall be presented:

| Field | Description |
| --- | --- |
| Project Name & ID | Unique identifier |
| Original Budget (INR) | Approved budget at project initiation |
| Revised Budget (INR) | Post-change-request budget |
| Cumulative Actual Spend (INR) | Actual expenditure till reporting date |
| Cumulative Committed Spend (INR) | POs raised but not yet invoiced |
| Forecast Spend at Completion (INR) | Estimated total spend |
| Variance (%) | (Forecast - Revised Budget) / Revised Budget * 100 |
| Budget Status | On Track / Watch / Alert / Critical |

6. Benefit Realisation Framework

6.1 Benefit Categories

| Benefit Type | Examples | Measurement Period |
| --- | --- | --- |
| Financial | Cost reduction, revenue increase, ROI | Quarterly |
| Operational | Process efficiency, error reduction, SLA improvement | Monthly |
| Strategic | Market share, customer satisfaction, regulatory compliance | Annual |
| Technology | System uptime, scalability, data quality | Monthly |

6.2 Benefit Realisation Tracking

| Phase | Activity | Deliverable |
| --- | --- | --- |
| Pre-Initiation | Define expected benefits in business case | Benefits Realisation Plan |
| During Project | Track leading indicators | Benefits Tracking Dashboard |
| At Closure | Validate benefits achieved | Benefits Realisation Report |
| Post-Closure (6-12 months) | Sustainment review | Post-Implementation Review |

6.3 Benefit Realisation Metrics

| Metric | Target | Tracking Period | Owner |
| --- | --- | --- | --- |
| Project ROI (Net Benefits / Total Cost) | > 20% | Annually | CFO |
| Cost Savings (INR) | As approved in business case | Quarterly | Project Sponsor |
| Efficiency Gain (FTE hours saved) | As approved in business case | Monthly | Operations Head |
| Customer Adoption Rate | As approved in business case | Monthly | Digital Banking Head |
| Error Rate Reduction | > 50% from baseline | Monthly | Quality Assurance |

7. Project Reporting Requirements

7.1 Standard Project Status Report (to be submitted 3 days before ITSC meeting)

| Section | Content |
| --- | --- |
| Executive Summary | Key achievements, risks, decisions required |
| Schedule Status | Planned vs Actual timeline with milestones |
| Budget Status | Budget vs actual with variance explanation |
| Risk Register | Top 5 risks with mitigation actions |
| Issues Log | Open issues with severity and owner |
| Benefit Tracking | Benefits realisation progress |
| Resource Status | Team composition, vacancies, attrition |
| Next Period Plan | Key activities for next reporting period |
| Decisions Required | Specific items for ITSC decision |

7.2 Project Categorisation for ITSC Review

| Category | Budget Range | Review Frequency | Escalation Level |
| --- | --- | --- | --- |
| Mega Project | > INR 50 Crore | Monthly + Quarterly Deep-Dive | Board / IT Strategy Committee |
| Major Project | INR 10 – 50 Crore | Monthly | IT Steering Committee |
| Standard Project | INR 2 – 10 Crore | Monthly (summary) | IT Steering Committee |
| Minor Project | < INR 2 Crore | Exception-based | Functional Head |

8. Escalation Protocol

| Escalation Level | Trigger | Action | Timeline |
| --- | --- | --- | --- |
| Level 1 – Project Manager | Schedule slippage > 10%, budget variance > 10% | Recovery plan | 5 working days |
| Level 2 – Project Sponsor | Schedule slippage > 20%, budget variance > 15%, risk score = 4 | Sponsor review + ITSC notification | 3 working days |
| Level 3 – IT Steering Committee | Risk score = 5, Critical vendor failure, compliance breach | Emergency meeting | 24 hours |
| Level 4 – IT Strategy Committee | Project failure risk, regulatory penalty exposure | Board notification | Immediate |

9. Document Templates Annexure

The following templates form part of this SOP and shall be used by all material IT projects:

| Template | Reference | Purpose |
| --- | --- | --- |
| Project Risk Register | BMBL/PMO/TMPL/007 | Risk identification and tracking |
| Budget Variance Report | BMBL/PMO/TMPL/008 | Budget performance monitoring |
| Benefits Realisation Plan | BMBL/PMO/TMPL/009 | Benefit definition and tracking |
| Project Status Report | BMBL/PMO/TMPL/010 | Monthly status reporting |
| Milestone Gate Checklist | BMBL/PMO/TMPL/011 | Stage-gate approval |

10. Compliance and Audit

| Requirement | Frequency | Evidence |
| --- | --- | --- |
| ITSC meeting minutes review | Monthly | Signed minutes |
| Project risk register audit | Quarterly | Audit sign-off |
| Budget variance reconciliation | Monthly | CFO certification |
| Benefit realisation validation | Bi-Annual | Internal audit report |
| SOP compliance check | Semi-Annual | Compliance dashboard |

11. Version History and Approval

| Approval Authority | Date | Decision Reference |
| --- | --- | --- |
| IT Strategy Committee | 28 May 2024 | ITSC/2024/015 |
| Chief Information Officer | 25 May 2024 | CIO/APP/2024/092 |

END OF DOCUMENT

*This SOP is the property of Bharat Mercantile Bank Limited. Unauthorised reproduction or distribution is prohibited.*