## Report
Action Para Details :-
Supervised Entity Name | Sr.No. | Action para Id | Action Para Description/Observation | Actual Due Date | Extended Due Date | Response Type | Is Resubmission Required | SE Status | Status | Regulatory Internal Comments By RBI | Regulatory Compliance Level Comments By RBI | Internal Comments By SSM And Higher Authority | Compliance Level Comments By SSM And Higher Authority | SE Response1 | 1st SSM Comment for SE | SE Response2 | 2nd SSM Comment for SE | SE Response3 | 3rd SSM Comment for SE | SE Response4 | 4th SSM Comment for SE | SE Response5 | 5th SSM Comment for SE | SE Response6 | 6th SSM Comment for SE | SE Response7 | 7th SSM Comment for SE | SE Response8 | 8th SSM Comment for SE | SE Response9 | 9th SSM Comment for SE | SE Response10 | 10th SSM Comment for SE | SE Response11 | 11th SSM Comment for SE | SE Response12 | 12th SSM Comment for SE | SE Response13 | 13th SSM Comment for SE | SE Response14 | 14th SSM Comment for SE | SE Response15 | 15th SSM Comment for SE
Rashtriya Setu Bank Limited | 1 | 3.1.1 | Several Board-approved cyber and modernisation initiatives slipped materially against committed timelines; milestone-based tracking with escalation for slippage was absent. | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Rashtriya Setu Bank Limited | 2 | 3.2.1 | A significant number of End-of-Life / End-of-Support servers and databases were active in the environment without a documented upgrade / replacement plan or interim compensating controls: | 29/01/2026 |  | Text | No | Complied | Complied
Rashtriya Setu Bank Limited | 3 | 3.2.2 | The CBS application was not included in the application inventory and multiple decommissioned applications were not removed from the inventory. | 29/01/2026 |  | Text | No | Complied | Not Complied
Rashtriya Setu Bank Limited | 4 | 3.3.1 | Operating-system patches released in earlier years were still missing on multiple servers, breaching the defined patch TAT; a tracker for database patching was not maintained. | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Rashtriya Setu Bank Limited | 5 | 3.3.2 | A centralized change-management function was not established and post-implementation review was not evidenced for a large number of network changes. | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Rashtriya Setu Bank Limited | 6 | 3.4.1 | Administrative access to the legacy CBS was not routed through a PAM solution, shared / default administrator accounts were in use, and periodic access recertification was infrequent. | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Rashtriya Setu Bank Limited | 7 | 3.5.1 | Segregation and hardening of the SWIFT environment and daily independent reconciliation of SWIFT messages with the CBS were not fully in place. | 29/01/2026 |  | Text | No | Complied | Complied
Rashtriya Setu Bank Limited | 8 | 3.5.2 | Users were allocated conflicting roles across SWIFT, Treasury and the CBS in violation of the four-eye principle; maker-checker was not enabled for adding new users to the messaging application. | 29/01/2026 |  | Text | No | Complied | Not Complied
Rashtriya Setu Bank Limited | 9 | 3.5.3 | Adequate time / holiday restrictions for processing SWIFT messages were not configured at the application level. | 29/01/2026 |  | Text | No | Complied | Not Complied
Rashtriya Setu Bank Limited | 10 | 3.6.1 | Network segmentation between corporate, payment and SWIFT environments was incomplete and firewall rule review was ineffective (rules with destination ‘ANY’, insecure ports). | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Rashtriya Setu Bank Limited | 11 | 3.7.1 | The outsourced SOC had not onboarded all critical applications and CBS privileged-user logs; closure timelines for SOC incidents were not defined. | 29/01/2026 |  | Text | No | Not Complied | Not Complied
Rashtriya Setu Bank Limited | 12 | 3.8.1 | Core technology operations were heavily concentrated with a single long-tenure vendor without a documented, tested exit / step-in arrangement. | 29/01/2026 |  | Text | No | Complied | Not Complied
Rashtriya Setu Bank Limited | 13 | 3.9.1 | DR drills did not cover all critical applications and switchover for certain government-business systems was untested. | 29/01/2026 |  | Text | No | Complied | Complied
Rashtriya Setu Bank Limited | 14 | 3.10.1 | Adaptive / risk-based authentication and real-time fraud monitoring on digital channels lagged the bank's transaction volumes, which was non-adherence to the authentication / fraud-risk provisions of the DPSC Master Direction. | 29/01/2026 |  | Text | No | Not Complied | Not Complied